Snow College’s NWCCU Accreditation Cycle/Planning Calendar
in preparation of the Year Seven full accreditation visit

2019—Preparation for Year Seven

- January:  Institutional Portfolio and Mission Fulfillment update presented to Board of Trustees

- May:  Recommendation 2 Ad Hoc Progress Update report #3 submitted to NWCCU

- June:  Mission Fulfillment Scorecard and Detail report presented to Board of Trustees

- July:  Year Seven Self-Study rough draft completed

- August:  Institutional Annual Report submitted

- Fall Semester:  Review of Year Seven rough draft.  This will include faculty, staff, and student representation

- October:  IR Director serves as a NWCCU evaluator to Pierce College

- November:  Participation in LDS Business College’s Year Seven “mock” site visit (their review is spring 2020).

- November:  IR Director attends NWCCU annual meeting (Seattle, WA)

2020—Year Seven Full Accreditation Visit

- January:  Institutional Portfolio and Mission Fulfillment update presented to Board of Trustees

- Spring Semester:  Year Seven Self Study in Final Draft (this will include information and review by faculty, staff, and students).

- Spring Semester:  Align final report information with on-line and on-site presence (i.e. policies/procedures).

- May:  submit any anticipated Ad Hoc reports

- June: Mission Fulfillment Scorecard and Detail report presented to Board of Trustees

- June/July:  Snow College will host a “mock” site visit in preparation of the fall semester visit.

- Summer:  Finalize dates for on-site visit

- August:  Institutional Annual Report submitted

- Fall semester (early):  submit finalized Year Seven Self-Evaluation

- Fall semester (October?):  Official on-site visit—Snow College hosts 4 to 5 on-site evaluators for a comprehensive review.  Site-visit will last 3-4 days. Actual dates TBA

- Fall semester:  Snow College will receive a draft report of findings for checking errors of fact only.

- November:  IR Director attends NWCCU annual meeting (Seattle, WA)

2021—Preparation of Year One Mission and Core Themes 
(this is the start of a new seven-year cycle)

- January:  Institutional Portfolio and Mission Fulfillment update presented to Board of Trustees

- Spring Semester:  Snow College will be informed of its re-accreditation sometime during the semester.

- Spring Semester:  Snow College can commence to re-evaluate its mission and core themes preparatory to submitting its Year One Mission and Core Themes report.

- Spring Semester:  Snow College will merge/align/coordinate re-evaluated mission and core themes with the institution’s strategic plan.

- June:  Presentation of new mission and core themes to Board of Trustees

- August:  Institutional Annual Report submitted

- Fall Semester:  Snow College establishes is new Mission and Core Themes complete with objectives and measurable KPIs prior to submitting its Year One Mission and Core Themes report.

- January:  Institutional Portfolio and Mission Fulfillment scorecard associated with re-evaluated core themes, objectives and KPIs.

2024—Mid-Cycle Report and Evaluation

2028—Year Seven Comprehensive Self Evaluation for re-accreditation

Internal reporting regarding mission fulfillment:

The main cycle repeats with the January Institutional Portfolio and Mission Fulfillment scorecard presented to the Board of Trustees; the June Mission Fulfillment Detail report presented to the Board of Trustees; and the August Annual Institutional report submitted to NWCCU.

- Annual Ad Hoc reports (when requested) submitted in May

- Annual Institutional report submitted to NWCCU in August

- Bi-annual reports to Board of Trustees in January and June

- Semester reports/meetings with various faculty, staff, and student leadership groups and at-large groups, including external stakeholders.